## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team | 2026-07-06 | The project required a stable relational data foundation for users, projects, customer feedback and application context. | Sprint 1 | Akhila | Standards | Designed and maintained the PostgreSQL data foundation and integrated the structured feedback/project data with the backend services. | 2026-07-03 | Closed | Relational data layer operational and used by downstream analytics and AI services.
2 | Team | 2026-07-06 | The initial product workflow required integration between authentication, backend APIs, database services and the frontend application. | Sprint 1 | Madhu / Adnan | Others | Implemented and integrated the authentication, API and frontend communication flow so the Product Manager can access the unified workspace. | 2026-07-03 | Closed | End-to-end authenticated application workflow verified.
3 | Team | 2026-07-13 | Analytics required reliable structured feedback data to calculate themes, trends, feature requests and priority signals. | Sprint 2 | Harshita / Akhila | Others | Integrated the analytics workflow with the PostgreSQL feedback dataset and implemented processing for clustering, trends, feature aggregation and priority scoring. | 2026-07-10 | Closed | Analytics outputs are available to the Product Manager through the application.
4 | Team | 2026-07-13 | Product analytics outputs needed to be presented in an actionable form rather than as raw feedback records. | Sprint 2 | Harshita / Adnan | User Interface | Implemented dashboard analytics views for KPIs, trends, themes, friction points and product insights. | 2026-07-10 | Closed | Product analytics and insights are accessible through the live frontend.
5 | Team | 2026-07-29 | Copilot AI responses required grounding with relevant customer feedback instead of relying only on the LLM's generic context. | Sprint 3 | Gagandeep | Others | Connected ContextBuilder vector retrieval to the Copilot streaming pipeline and injected relevant Qdrant feedback chunks into the RAG prompt | 2026-07-19 | Closed | Qdrant retrieves relevant evidence chunks and grounded Copilot responses are runtime verified.
6 | Team | 2026-07-29 | PRD generation required stronger contextual grounding and a standardized structured output format | Sprint 3 | Gagandeep | Standards | Enhanced ContextBuilder prompt construction with retrieved evidence, analytics context, GFM evidence tables, non-goals, rollout information and structured PRD requirements. | 2026-07-19 | Closed | Generated PRDs contain structured metadata, evidence, requirements, acceptance scenarios and rollout information.
7 | Team | 2026-07-29 | AI availability could be interrupted when the primary Gemini model encountered quota, rate-limit or temporary availability errors. | Sprint 3 | Gagandeep | Others | Implemented Gemini model fallback handling that rotates through configured fallback models when 503, 429 or resource exhaustion errors occur. | 2026-07-19 | Closed | Model fallback sequence verified during runtime testing.
8 | Team | 2026-08-11 | Qdrant container startup health verification was unreliable and could create startup race conditions between infrastructure services. | Sprint 4 | Gagandeep / Adnan | Others | Replaced the Qdrant healthcheck with low-overhead socket-level verification against port 6333 and improved service startup reliability. | 2026-08-01 | Closed | Qdrant container reports healthy and vector retrieval operates correctly.
9 | Team | 2026-08-11 | Copilot and PRD streaming responses could suffer from incorrect SSE buffering or newline/data parsing, affecting structured Markdown rendering. | Sprint 4 | Gagandeep / Adnan | User Interface | Normalized SSE JSON delta extraction and implemented a non-destructive streaming buffer parser in the frontend service layer. | 2026-08-01 | Closed | Live token streaming verified for both Copilot and PRD Generator.
10 | Team | 2026-08-11 | Markdown tables generated by the AI PRD output were previously rendered as collapsed plain-text lines instead of structured tables. | Sprint 4 | Gagandeep / Adnan | User Interface | Integrated ReactMarkdown with remark-gfm and structured Markdown rendering components in AskCopilot and PRDGenerator. | 2026-08-01 | Closed | GFM tables, headings, code blocks and blockquotes render correctly.
11 | Team | 2026-08-11 | Generated PRDs were not automatically persisted as reusable product artifacts after AI generation. | Sprint 4 | Adnan / Gagandeep | User Interface | Implemented prdStorage.ts and integrated automatic post-stream persistence into PRDGenerator.tsx for generated Markdown, metadata and indexed PRD records. | 2026-08-01 | Closed | Generated PRDs persist across browser refreshes and are available through the Dashboard.
12 | Team | 2026-08-11 | Recently generated PRDs were not dynamically reflected in the Dashboard Recent PRDs section and document count. | Sprint 4 | Adnan | User Interface | Updated Dashboard.tsx to aggregate newly generated PRDs, synchronize document counters and refresh stored data on reload/window focus. | 2026-08-01 | Closed | Dashboard reflects newly generated PRDs and synchronized document totals.
13 | Team | 2026-08-11 | Product Manager required the ability to review and modify AI-generated PRDs before export. | Sprint 4 | Adnan | User Interface | Added inline Markdown editor mode with save/preview controls in the PRD Generator. | 2026-08-01 | Closed | PRDs can be edited, previewed, saved and exported.
14 | Team | 2026-08-11 | Copilot conversations previously lacked persistent session history and long-term conversational context across sessions. | Sprint 4 | Adnan | Others | Added PostgreSQL migrations and services for chat sessions, conversation messages and persistent memory, along with frontend session management. | 2026-08-01 | Closed | Multiple chat sessions and persistent conversation history are supported.
15 | Team | 2026-08-11 | Older chat history could exceed the active context window and consume excessive prompt context. | Sprint 4 | Adnan / Gagandeep | Others | Implemented a 3000-token recent-message sliding window and rolling session summarization for older conversation history. | 2026-08-01 | Closed | Recent dialogue and compressed historical context are assembled before AI generation.
16 | Team | 2026-08-11 | The Copilot required relevant information from previous product discussions to be available in future sessions. | Sprint 4 | Adnan / Gagandeep | Others | Implemented MemoryExtractorService and Qdrant user_memory retrieval to store and retrieve semantically relevant product facts, preferences and constraints. | 2026-08-01 | Closed | Cross-session memory retrieval is integrated into the prompt assembly pipeline.
17 | Team | 2026-08-24 | Firebase workspace listener was failing with a FirebaseError when querying workspace records. | Sprint 5 | Adnan / Madhu | Others | Investigated the Firestore query and deployed the required composite index on the workspaces collection using userId (Ascending) and createdAt (Descending). | 2026-08-16 | Closed | Firebase workspace synchronization verified successfully.
18 | Team | 2026-08-24 | Production frontend requests were affected by hardcoded localhost:8000 backend URLs, preventing correct cloud communication. | Sprint 5 | Adnan / Madhu | User Interface | Refactored settingsService.ts, feedbackService.ts and chatService.ts to use VITE_API_BASE_URL with trailing-slash normalization. | 2026-08-16 | Closed | Frontend API communication works with the deployed Render backend.
19 | Team | 2026-08-24 | Production API requests from the Vercel frontend were affected by insufficient CORS origin handling. | Sprint 5 | Madhu | Standards | Updated FastAPI CORSMiddleware with dynamic origin validation and support for Vercel production and preview domains. | 2026-08-16 | Closed | Production frontend-backend communication verified.
20 | Team | 2026-08-24 | Refreshing frontend routes directly on Vercel resulted in 404 NOT_FOUND errors because SPA routes were not rewritten correctly. | Sprint 5 | Adnan | User Interface | Added root-level vercel.json rewrite configuration to route SPA requests to index.html while preserving backend API proxy routes. | 2026-08-16 | Closed | Direct route navigation and browser refresh verified
21 | Team | 2026-08-24 | Backend database connection failed because psycopg2 configuration was incompatible with the asynchronous SQLAlchemy AsyncEngine and produced an invalid ssl connection option error. | Sprint 5 | Madhu | Standards | Updated database configuration to use postgresql+asyncpg with the required native TLS/SSL connection handling. | 2026-08-16 | Closed | Neon PostgreSQL connection and seed pipeline verified
22 | Team | 2026-08-24 | Database initialization required reproducible population of project entities, telemetry metrics and customer feedback for production deployment. | Sprint 5 | Akhila / Madhu | Others | Executed the database seed pipeline and populated the Neon PostgreSQL database with required project, telemetry and feedback data. | 2026-08-16 | Closed | Production database seeded and active. ¦
23 | Team | 2026-08-24 | Repository configuration created namespace/fork conflicts that could interfere with clean project submission and evaluation | Sprint 5 | Gagandeep / Adnan | Standards | Resolved GitHub repository namespace conflicts and configured the repository for clean fork-based submission. | 2026-08-16 | Closed | Repository synchronized and prepared for project evaluation.
24 | Team | 2026-08-24 | Backend route naming changes could break existing frontend or previously configured clients using top-level API routes. | Sprint 5 | Madhu | Standards | Added backward-compatible route aliases for analytics, AI, sessions, copilot, projects and feedback endpoints. | 2026-08-16 | Closed | Existing and updated route paths remain supported.
25 | Team | 2026-08-24 | The complete application required reliable deployment across frontend, backend, relational database, vector database and authentication infrastructure. | Sprint 5 | Gagandeep / Adnan / Madhu / Akhila / Harshita | Others | Completed cloud deployment using Vercel, Render, Neon PostgreSQL, Qdrant Cloud, Gemini API and Firebase Authentication, followed by end-to-end verification. | 2026-08-16 | Closed | Production deployment completed and live system verified.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others