## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Initial integration between the frontend, backend, authentication and PostgreSQL data layer was not yet established. | Must | PostgreSQL database and backend integration | Akhila | Completed
Sprint 1 | Sprint 1 | US-02 | As a Product Manager, I want to authenticate and access my product workspace so that I can securely use the application's features. | Must | Firebase Authentication, frontend and backend integration | Madhu / Adnan | Completed
Sprint 1 | Sprint 1 | US-03 | As a Product Manager, I want customer feedback to be associated with projects so that product analysis can be performed using structured feedback data. | Must | PostgreSQL data model and project structure | Akhila / Madhu | Completed
Sprint 1 | Sprint 1 | US-04 | s a Product Manager, I want a unified frontend workspace so that I can access product data and application functionality from a single interface. | Must | Authentication and backend APIs | Adnan | Completed
Sprint 2 | Sprint 2 | US-05 | As a Product Manager, I want the system to process customer feedback so that raw feedback can be converted into meaningful product intelligence. | Must | PostgreSQL feedback dataset | Harshita / Akhila | Completed
Sprint 2 | Sprint 2 | US-06 | As a Product Manager, I want similar feedback to be grouped into themes so that recurring customer problems and opportunities can be identified efficiently. | Must | Feedback ingestion and analytics processing | Harshita | Completed
Sprint 2 | Sprint 2 | US-07 | As a Product Manager, I want to analyze feedback trends over time so that I can identify increasing, decreasing or recurring customer issues. | Should | Structured feedback with timestamps | Harshita | Completed
Sprint 2 | Sprint 2 | US-08 | As a Product Manager, I want feature requests to be aggregated and prioritized so that I can identify which product opportunities deserve attention first. | Must | Theme extraction and feedback analytics | Harshita / Akhila | Completed
Sprint 2 | Sprint 2 | US-09 | As a Product Manager, I want analytics KPIs, themes, trends and friction points displayed visually so that I can understand product health without manually reading raw feedback | Must | Analytics engine and frontend integration | Harshita / Adnan | Completed
Sprint 2 | Sprint 2 | US-10 | As a Product Manager, I want analytics insights to be accessible through the product dashboard so that I can use them during product planning and decision-making. | Must | Backend analytics APIs and frontend | Harshita / Adnan | Completed
Sprint 3 | Sprint 3 | US-11 | As a Product Manager, I want the AI Copilot to retrieve relevant customer feedback so that its answers are grounded in actual product evidence. | Must | Qdrant vector database and feedback embeddings | Gagandeep | Completed
Sprint 3 | Sprint 3 | US-12 | As a Product Manager, I want the AI Copilot to combine retrieved evidence with product context so that it can answer product questions more accurately than a generic chatbot. | Must | RAG ContextBuilder and Gemini API | Gagandeep | Completed
Sprint 3 | Sprint 3 | US-13 | As a Product Manager, I want to generate structured PRDs from product insights so that customer problems can be converted into actionable product requirements. | Must | Analytics insights, RAG context and Gemini AP | Gagandeep | Completed
Sprint 3 | Sprint 3 | US-14 | As a Product Manager, I want generated PRDs to include requirements, evidence, acceptance scenarios, non-goals and rollout information so that the document can support actual product development. | Should | PRD prompt builder and retrieved product context | Gagandeep | Completed
Sprint 3 | Sprint 3 | US-15 | As a Product Manager, I want the AI system to use fallback models when the primary Gemini model is unavailable or rate-limited so that AI functionality remains resilient. | Must | Gemini API and configured fallback models | Gagandeep | Completed
Sprint 4 | Sprint 4 | US-16 | As a Product Manager, I want reliable Qdrant service health checks so that semantic retrieval starts consistently without infrastructure race conditions. | Should | Dockerized Qdrant service | Gagandeep / Adnan | Completed
Sprint 4 | Sprint 4 | US-17 | As a Product Manager, I want Copilot and PRD responses to stream in real time so that I can see AI output without waiting for the complete response. | Must | FastAPI SSE streaming and frontend parser | Gagandeep / Adnan | Completed
Sprint 4 | Sprint 4 | US-18 | As a Product Manager, I want AI-generated Markdown tables, headings, code blocks and other formatting rendered correctly so that generated product documents are readable and professional. | Should | ReactMarkdown and remark-gfm | Gagandeep / Adnan | Completed
Sprint 4 | Sprint 4 | US-19 | As a Product Manager, I want generated PRDs to be automatically persisted so that I can access them again after generation or browser refresh. | Must | PRD storage service and persistence layer | Adnan / Gagandeep | Completed
Sprint 4 | Sprint 4 | US-20 | As a Product Manager, I want recently generated PRDs to appear automatically in the dashboard so that my document library remains synchronized with newly created artifacts. | Should | PRD persistence and dashboard synchronization | Adnan | Completed
Sprint 4 | Sprint 4 | US-21 | As a Product Manager, I want to edit and preview AI-generated PRDs before exporting them so that I can refine the document according to my requirements. | Must | PRD persistence and Markdown editor | Adnan | Completed
Sprint 4 | Sprint 4 | US-22 | As a Product Manager, I want multiple Copilot chat sessions with persistent history so that I can maintain separate product discussions over time. | Must | PostgreSQL chat session and message storage | Adnan | Completed
Sprint 4 | Sprint 4 | US-23 | As a Product Manager, I want older conversation history to be summarized so that long-running conversations do not exceed the active AI context window. | Should | PostgreSQL session summaries and prompt assembly | Adnan / Gagandeep | Completed
Sprint 4 | Sprint 4 | US-24 | s a Product Manager, I want important product facts, preferences and constraints from previous conversations to be remembered so that future Copilot sessions can maintain relevant context | Must | Qdrant user_memory and MemoryExtractorService | Adnan / Gagandeep | Completed
Sprint 5 | Sprint 5 | US-25 | As a Product Manager, I want my workspace information to synchronize correctly through Firebase so that the application displays the correct workspace state. | Must | Firebase Firestore and composite indexing | Adnan / Madhu | Completed
Sprint 5 | Sprint 5 | US-26 | As a Product Manager, I want the deployed frontend to communicate with the production backend instead of localhost so that the application works correctly in the cloud | Must | Vercel, Render and environment configuration | Madhu | Completed
Sprint 5 | Sprint 5 | US-27 | As a Product Manager, I want secure cross-origin communication between the frontend and backend so that production API requests are accepted only from configured application origins. | Must | FastAPI CORS configuration and Vercel deployment | Madhu | Completed
Sprint 5 | Sprint 5 | US-28 | As a Product Manager, I want frontend routes to work correctly after browser refresh so that navigation remains reliable in the deployed single-page application. | Must | Vercel SPA rewrite configuration | Adnan | Completed
Sprint 5 | Sprint 5 | US-29 | As a Product Manager, I want the production backend to connect reliably to PostgreSQL so that application data and analytics remain available after deployment. | Must | Neon PostgreSQL and asyncpg | Madhu | Completed
Sprint 5 | Sprint 5 | US-30 | As a Product Manager, I want the production database to be populated with required projects, telemetry and feedback data so that the deployed application can operate with realistic product information. | Must | Neon PostgreSQL and seed pipeline | Akhila / Madhu | Completed
Sprint 5 | Sprint 5 | US-31 | As a Product Manager, I want existing API routes to remain compatible after backend changes so that frontend and previously configured clients continue to function correctly. | Should | FastAPI route structure | Madhu | Completed
Sprint 5 | Sprint 5 | US-32 | As a project team, we want the repository to be correctly configured for evaluation and fork-based submission so that the project can be submitted without repository namespace conflicts. | Must | GitHub repository configuration | Gagandeep / Adnan | Completed
Sprint 5 | Sprint 5 | US-33 | As a Product Manager, I want the complete application deployed across frontend, backend, database, vector database, authentication and AI infrastructure so that I can use the complete product in a production environment. | Must | Vercel, Render, Neon, Qdrant, Firebase and Gemini | Gagandeep / Adnan / Madhu / Akhila / Harshita | Completed
Sprint 5 | Sprint 5 | US-34 | As a Product Manager, I want the deployed system to be verified end-to-end so that authentication, feedback, analytics, Copilot, memory, PRD generation and persistence work together as one product workflow. | Must | All integrated project modules | Gagandeep / Adnan / Madhu / Akhila / Harshita | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 277 | 37 | 33 | 37 | 36 | 33 | 30 | 26 | 20 | 15 | 8 | 2 | 1 | 0 | 0
SPRINT BACKLOGS
US-01 | T-01 | Define overall AI Product Manager Copilot architecture and end-to-end product workflow | 2026-07-03 | 2026-07-06 | Gagandeep | Architecture / Planning | Completed | 8 | 2 | 2 | 1 | 1 | 1 | 1 | — | — | — | — | — | — | — | —
US-01 | T-02 | Design PostgreSQL data foundation for users, projects and customer feedback | 2026-07-03 | 2026-07-06 | Akhila | Database Design | Completed | 10 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | — | — | — | — | — | — | —
US-01 | T-03 | Establish initial backend API and authentication integration | 2026-07-03 | 2026-07-06 | Madhu | Backend / Authentication | Completed | 10 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | — | — | — | — | — | — | —
US-01 | T-04 | Establish frontend application and backend communication flow | 2026-07-03 | 2026-07-06 | Adnan | Frontend Integration | Completed | 10 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | — | — | — | — | — | — | —
US-01 | T-05 | Establish analytics requirements for feedback clustering, trends and prioritization | 2026-07-03 | 2026-07-06 | Harshitha | Analytics Planning | Completed | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | — | — | — | — | — | — | —
US-02 | T-06 | Integrate PostgreSQL feedback data with analytics processing | 2026-07-10 | 2026-07-13 | Akhila / Harshitha | Data + Analytics Integration | Completed | 12 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | — | — | — | — | —
US-02 | T-07 | Implement theme clustering and recurring customer issue identification | 2026-07-10 | 2026-07-13 | Harshita | Theme Analytics | Completed | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | — | — | — | — | —
US-02 | T-08 | Implement trend analysis and feature aggregation | 2026-07-10 | 2026-07-13 | Harshita | Analytics | Completed | 10 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | — | — | — | — | — | —
US-02 | T-09 | Implement analytics dashboard views for KPIs, trends and product insights | 2026-07-10 | 2026-07-13 | Harshita / Adnan | Analytics UI | Completed | 12 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | — | — | — | —
US-03 | T-10 | Implement priority scoring for product issues and opportunities | 2026-07-19 | 2026-07-29 | Harshita | Prioritization | Completed | 8 | bar: Day 1 to Day 14
US-03 | T-11 | Implement Qdrant vector retrieval for relevant customer feedback | 2026-07-19 | 2026-07-29 | Gagandeep | RAG / Vector Search | Completed | 12 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | — | — | — | — | —
US-03 | T-12 | Integrate RAG retrieval into the AI Copilot context pipeline | 2026-07-19 | 2026-07-29 | Gagandeep | AI / RAG | Completed | 12 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | — | — | — | — | —
US-03 | T-13 | Implement Gemini AI streaming response generation | 2026-07-19 | 2026-07-29 | Gagandeep | Generative AI | Completed | 10 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | — | — | — | — | —
US-03 | T-14 | Implement Gemini model fallback handling for quota and availability errors | 2026-07-19 | 2026-07-29 | Gagandeep | AI Reliability | Completed | 6 | bar: Day 1 to Day 14
US-04 | T-15 | Implement persistent Copilot chat sessions and message storage | 2026-08-01 | 2026-08-11 | Adnan / Gagandeep | Chat / Persistence | Completed | 12 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | — | — | — | —
US-04 | T-16 | Implement rolling conversation summary and context-window management | 2026-08-01 | 2026-08-11 | Adnan / Gagandeep | Memory Management | Completed | 10 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | — | — | — | — | —
US-04 | T-17 | Implement long-term semantic memory using Qdrant | 2026-08-01 | 2026-08-11 | Adnan / Gagandeep | Persistent Memory | Completed | 12 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | — | — | — | —
US-04 | T-18 | Implement Copilot interface features including session management, sources and memories | 2026-08-01 | 2026-08-11 | Adnan | Frontend / Copilot UI | Completed | 12 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | — | — | — | —
US-04 | T-19 | Implement SSE parser and real-time Markdown/GFM rendering | 2026-08-01 | 2026-08-11 | Gagandeep / Adnan | Frontend / Streaming | Completed | 11 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | — | — | — | —
US-04 | T-20 | Implement AI-generated PRD pipeline with contextual evidence | 2026-08-01 | 2026-08-11 | Gagandeep | PRD Generation | Completed | 12 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | — | — | —
US-04 | T-21 | Implement PRD editing, preview, persistence and export | 2026-08-01 | 2026-08-11 | Adnan / Gagandeep | PRD Workspace | Completed | 12 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | — | — | — | —
US-05 | T-22 | Seed production PostgreSQL database with project, telemetry and feedback data | 2026-08-16 | 2026-08-24 | Akhila / Madhu | Database / Deployment | Completed | 8 | bar: Day 1 to Day 14
US-05 | T-23 | Resolve asynchronous PostgreSQL driver and TLS connection configuration | 2026-08-16 | 2026-08-24 | Madhu | Backend / Database | Completed | 6 | bar: Day 1 to Day 14
US-05 | T-24 | Configure Firebase workspace synchronization and Firestore indexing | 2026-08-16 | 2026-08-24 | Adnan / Madhu | Authentication / Workspace | Completed | 6 | bar: Day 1 to Day 14
US-05 | T-25 | Configure production frontend-backend API communication and CORS | 2026-08-16 | 2026-08-24 | Madhu / Adnan | Deployment / Integration | Completed | 8 | bar: Day 1 to Day 14
US-05 | T-26 | Configure Vercel SPA routing and production frontend deployment | 2026-08-16 | 2026-08-24 | Adnan | Deployment / Frontend | Completed | 6 | bar: Day 1 to Day 14
US-05 | T-27 | Improve Qdrant health verification and deployment reliability | 2026-08-16 | 2026-08-24 | Gagandeep / Adnan | Infrastructure | Completed | 6 | bar: Day 1 to Day 14
US-05 | T-28 | Resolve repository namespace/fork configuration for final submission | 2026-08-16 | 2026-08-24 | Gagandeep / Adnan | Repository Management | Completed | 4 | bar: Day 1 to Day 14
US-05 | T-29 | Perform end-to-end production deployment and verification | 2026-08-16 | 2026-08-24 | Gagandeep / Adnan / Akhila / Harshita / Madhu | Integration / Deployment | Completed | 12 | bar: Day 1 to Day 14
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial integration between the frontend, backend, authentication and PostgreSQL data layer was not yet established. | Defined the application architecture, established the PostgreSQL data foundation, and integrated authentication, backend APIs and frontend communication into the initial product workflow.
Sprint 1 | Day 2 | Structured project and customer feedback data required a reliable relational foundation for downstream analytics and AI features | Designed and maintained the PostgreSQL data model and integrated structured project and feedback data with the backend services.
Sprint 2 | Day 1 | Raw customer feedback could not directly provide actionable product insights without systematic processing. | Integrated the analytics workflow with PostgreSQL feedback data and implemented processing for themes, clustering, trends, feature aggregation and priority signals.
Sprint 2 | Day 2 | Analytics results needed to be presented in an understandable form instead of exposing raw feedback records to the Product Manager | Developed dashboard views for KPIs, trends, themes, friction points and product insights and connected them to the application workflow
Sprint 3 | Day 1 | AI Copilot responses risked being generic because the LLM did not automatically have access to relevant customer feedback and product evidence. | Connected Qdrant vector retrieval with the Copilot pipeline and injected relevant feedback evidence into the RAG prompt through the ContextBuilder.
Sprint 3 | Day 2 | AI generation could be interrupted by Gemini quota, rate-limit or temporary service availability failures. | Implemented Gemini model fallback handling for 503, 429 and resource-exhaustion conditions so generation can continue using configured fallback models.
Sprint 4 | Day 1 | Copilot and PRD streaming had issues with SSE buffering and Markdown parsing, while generated PRDs also required persistent storage and editing. | Implemented robust SSE buffer parsing, ReactMarkdown with GFM support, PRD persistence, inline Markdown editing, save/preview functionality and dashboard synchronization.
Sprint 4 | Day 2 | Long conversations could exceed the active context window, and important information from previous sessions could be lost. | Implemented the 3,000-token recent-message sliding window, rolling session summaries and Qdrant-based long-term semantic memory for relevant product facts and constraints.
Sprint 5 | Day1- 2 | Production deployment faced multiple cloud integration issues including Firebase workspace listener errors, hardcoded localhost API URLs, CORS restrictions, Vercel SPA 404s and PostgreSQL driver/SSL incompatibility. | Deployed the required Firestore composite index, standardized API URLs using VITE_API_BASE_URL, configured dynamic CORS, added Vercel SPA rewrites, migrated the database connection to postgresql+asyncpg, seeded Neon PostgreSQL and completed end-to-end production verification across Vercel, Render, Neon, Qdrant, Gemini and Firebase.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-03 | 2026-07-06 | Gagandeep | Start defining the AI architecture and integration requirements early so downstream components can align with the Copilot and RAG workflow. | Stop treating AI functionality as an isolated module without considering its integration with the database, backend and frontend | Continue coordinating the overall product architecture and maintaining the end-to-end product vision. | Defined the initial AI/Copilot direction and coordinated integration requirements across the team.
2 | Sprint 1 | 2026-07-03 | 2026-07-06 | Adnan | Start establishing frontend-backend integration patterns early to reduce later integration issues. | Stop relying on assumptions about backend routes and local development URLs when designing frontend services. | Continue focusing on usability and integration of the frontend with the application backend. | Implemented and integrated the initial frontend communication flow with the backend and authentication workflow
3 | Sprint 2 | 2026-07-10 | 2026-07-13 | Akhila | Start validating database structures and feedback data requirements together with the Analytics team before downstream processing. | Stop treating database work as independent from analytics and AI requirements. | Continue maintaining PostgreSQL as the structured source of truth for product data and feedback. | Integrated the structured PostgreSQL feedback/project data with the analytics workflow and supported the data foundation required for downstream processing.
4 | Sprint 2 | 2026-07-10 | 2026-07-13 | Harshita | Start validating analytics outputs with realistic feedback distributions and product-management use cases. | Stop presenting raw analytical calculations without connecting them to actionable product decisions. | Continue developing themes, trends, feature aggregation and priority signals that help Product Managers understand customer needs. | Implemented and integrated analytics processing for clustering, trends, feature aggregation and priority scoring, and worked with the frontend to expose actionable insights.
5 | Sprint 3 | 2026-07-19 | 2026-07-29 | Madhu | Start validating API, authentication and database connectivity against the eventual production environment earlier in development. | Stop depending only on local configuration when testing backend communication and integration. | Continue maintaining the backend API, authentication and integration layer between system components. | Strengthened backend integration and prepared the API/database communication flow required for the later production deployment and cloud migration.
6 | Sprint 4 | 2026-08-01 | 2026-08-11 | Gagandeep / Adnan | Start testing streaming, memory, retrieval and persistence together as a complete AI workflow rather than testing each feature independently. | Stop treating streaming and AI output rendering as separate concerns from frontend persistence and user experience. | Continue collaborating closely on RAG, SSE streaming, Qdrant integration, persistent memory and PRD generation. | Improved Qdrant health verification, normalized SSE streaming, implemented Markdown/GFM rendering, integrated persistent memory and completed PRD persistence and synchronization workflows.
7 | Sprint 5 | 2026-08-16 | 2026-08-24 | Gagandeep, Adnan, Akhila, Harshita & Madhu | Start performing production-oriented end-to-end verification earlier and maintain a shared deployment checklist for all infrastructure services. | Stop assuming that a feature working locally guarantees correct cloud behaviour. | Continue cross-functional collaboration, systematic debugging, integration testing and verification of the complete product workflow. | Resolved Firebase indexing, CORS, API URL, SPA routing and async PostgreSQL driver issues; seeded Neon PostgreSQL; verified Qdrant, Firebase, Gemini, Vercel and Render integration; and completed production deployment and end-to-end verification.